## Start Here
Databricks Data Engineering Journey — 6-Month Learning Tracker
26 weeks • ~10 hours/week • ~260 planned hours • Python, NumPy, Pandas, PySpark, Databricks and Delta Lake
How to use this workbook
1. Start with the 26-Week Roadmap sheet to see the weekly concepts, resources, project and expected deliverable.
2. In Daily Tracker, enter a planned date if useful, then update Actual Hours, Status and Notes after each session.
3. Status options: Not Started, In Progress, Blocked, Completed. Use the notes column to record links, blockers and lessons.
4. Planned hours are allocated as 1.5 hours for Days 1–6 and 1 hour for Day 7 = 10 hours/week. Move sessions around as needed.
5. Use the Progress Dashboard to track completion. Completion is based on marking daily tasks Completed.
6. Free-tier/platform features and URLs can change. Check current Databricks Free Edition limits before planning compute-heavy exercises.
7. Do not upload employer/client data or confidential code to a public repository. Use synthetic/public datasets.
Suggested weekly routine
Days 1–2 | Concepts + guided examples | 3 hours
Days 3–5 | Exercises + realistic data + debugging | 4.5 hours
Day 6 | Mini-project implementation | 1.5 hours
Day 7 | Finish deliverable + review | 1 hour
Learning outcome after 6 months
Target: working proficiency to build, test, troubleshoot and explain a production-style lakehouse pipeline. Advanced mastery requires continued practice beyond the planned 260 hours.

## Progress Dashboard
Learning Progress Dashboard
Overall Metrics
Planned learning hours | 260
Actual learning hours | 0
Daily sessions completed | 0
Total daily sessions | 182
Completion percentage | 0%
Hours progress percentage | 0%
Progress by week
Week | Theme | Completed sessions | Total sessions | Actual hours | Status
1 | Python basics and programming logic | 0 | 7 | 0 | Not Started
2 | Data structures and functions | 0 | 7 | 0 | Not Started
3 | Files, exceptions and reusable code | 0 | 7 | 0 | Not Started
4 | Advanced Python fundamentals and testing | 0 | 7 | 0 | Not Started
5 | NumPy fundamentals | 0 | 7 | 0 | Not Started
6 | Pandas DataFrames and data cleaning | 0 | 7 | 0 | Not Started
7 | Advanced Pandas transformations | 0 | 7 | 0 | Not Started
8 | Pandas performance and data analysis | 0 | 7 | 0 | Not Started
9 | Spark architecture and PySpark setup | 0 | 7 | 0 | Not Started
10 | PySpark DataFrame transformations | 0 | 7 | 0 | Not Started
11 | Joins, aggregations and windows | 0 | 7 | 0 | Not Started
12 | Spark internals and performance | 0 | 7 | 0 | Not Started
13 | Advanced PySpark patterns | 0 | 7 | 0 | Not Started
14 | Databricks workspace and notebooks | 0 | 7 | 0 | Not Started
15 | Delta Lake fundamentals | 0 | 7 | 0 | Not Started
16 | Lakehouse and medallion architecture | 0 | 7 | 0 | Not Started
17 | Incremental processing and CDC | 0 | 7 | 0 | Not Started
18 | Advanced performance optimization | 0 | 7 | 0 | Not Started
19 | Structured Streaming | 0 | 7 | 0 | Not Started
20 | Workflow orchestration and operations | 0 | 7 | 0 | Not Started
21 | Data quality, testing and governance | 0 | 7 | 0 | Not Started
22 | Deployment, reusable code and CI/CD | 0 | 7 | 0 | Not Started
23 | Capstone design and ingestion | 0 | 7 | 0 | Not Started
24 | Capstone business transformations | 0 | 7 | 0 | Not Started
25 | Capstone optimization and operations | 0 | 7 | 0 | Not Started
26 | Final deployment and portfolio | 0 | 7 | 0 | Not Started

## 26-Week Roadmap
Week | Month | Weekly Theme | Core Concepts to Learn | Resources / Practical Exercises | Mini-Project / Deliverable | Completion Evidence | Status | Notes
1 | Month 1 | Python basics and programming logic | Variables; primitive data types; type conversion; operators; conditionals; loops; notebook/script execution. | Official Python Tutorial; Google Colab or local Python. Exercises: 15–20 small problems on conditions, loops, calculations. | ETL validation utility: validate employee IDs and salaries; separate valid and rejected records. | Runnable script with 10+ test records. | Not Started
2 | Month 1 | Data structures and functions | Lists, tuples, sets, dictionaries; indexing/slicing; comprehensions; functions; parameters; return values; lambda; scope; nested JSON. | Python tutorial: data structures and functions. Exercises: normalize API-style JSON and write 10 functions. | API response transformer: extract customers, calculate order totals, group orders, identify duplicate IDs. | Reusable Python module with 5+ functions. | Not Started
3 | Month 1 | Files, exceptions and reusable code | CSV/JSON/text files; exceptions; logging; modules/packages; virtual environments; type hints; docstrings; OOP basics. | Python standard library docs. Exercises: malformed files, invalid values, missing files, line-by-line processing. | File-based ETL framework: read CSVs, validate schemas, consolidate outputs, quarantine rejects. | Configurable pipeline with logs and exception handling. | Not Started
4 | Month 1 | Advanced Python fundamentals and testing | Iterators/generators; decorators; context managers; shallow/deep copy; pytest; mocking basics; Git basics. | pytest docs and GitHub Skills. Exercises: tests for ETL utility and chunked file processing. | Production-style CSV processing package split into ingestion, validation, transformation, logging and config. | Git repository with tests, README, sample input/output. | Not Started
5 | Month 2 | NumPy fundamentals | ndarray; shape/dimensions; indexing; reshaping; broadcasting; vectorization; Boolean masks; aggregations; statistics. | NumPy beginner guide. Compare loops with vectorized operations on transaction data. | Transaction analytics engine for revenue, averages, outliers, percentiles and category summaries. | Notebook comparing loop and vectorized solutions. | Not Started
6 | Month 2 | Pandas DataFrames and data cleaning | Series/DataFrame/index; CSV/JSON/Excel/Parquet I/O; filtering; sorting; missing values; duplicates; data types; schema checks. | Pandas getting-started tutorials; Kaggle public dataset. Introduce nulls, duplicates and bad types. | Customer data cleansing pipeline standardizing names/emails, handling nulls and duplicates. | Cleaned Parquet dataset plus data-quality report. | Not Started
7 | Month 2 | Advanced Pandas transformations | groupby/agg/transform/apply; merge/join/concat; pivot/melt; dates; resampling; rolling windows; vectorized strings. | Pandas merging and groupby guides. Solve 15 SQL-style problems in Pandas. | Sales/customer analytics: join orders/customers/products; monthly revenue, repeat purchases, top products, lifetime spend. | Notebook with 8+ validated business metrics. | Not Started
8 | Month 2 | Pandas performance and data analysis | Memory usage; efficient dtypes; chunked CSV; profiling; plotting; distributions; correlations; outliers; Pandas vs Spark. | Pandas scaling guide. Benchmark increasing dataset sizes and chunked vs full-file processing. | Local data profiler reporting schema, nulls, duplicates, summaries and processing duration. | CLI profiler with chunked processing. | Not Started
9 | Month 3 | Spark architecture and PySpark setup | Distributed computing; driver/executors; partitions/tasks; SparkSession; lazy evaluation; transformations/actions; schemas; CSV/JSON/Parquet. | Apache Spark overview and SQL/DataFrame guide; Databricks Free Edition where available. Compare SQL/Pandas/PySpark. | First distributed ingestion pipeline with schema, filters and Parquet output. | PySpark notebook with schema, transformations and validation. | Not Started
10 | Month 3 | PySpark DataFrame transformations | select/filter/withColumn/when; casts; null handling; deduplication; built-in functions; expressions; schema enforcement. | Spark SQL/DataFrame guide. Rewrite 15 Pandas transformations in PySpark. | Transaction cleansing: standardized schema, quarantined invalid rows and rejection reasons. | Parameterized cleansing notebook with explicit schemas. | Not Started
11 | Month 3 | Joins, aggregations and windows | Inner/left/right/full/semi/anti joins; groupBy/agg; window specs; row_number/rank/dense_rank/lag/lead; business-key deduplication. | PySpark window function docs. Solve SQL interview problems in DataFrames. | Customer 360 with lifetime spend, latest purchase, top products and transaction rankings. | Curated customer analytics table reconciled against SQL. | Not Started
12 | Month 3 | Spark internals and performance | Narrow/wide transformations; shuffles; jobs/stages/tasks; explain/physical plans; Spark UI; repartition/coalesce; broadcast; cache; skew. | Spark tuning guide. Compare joins and inspect plans, shuffle and runtime metrics. | Performance lab comparing 2–3 implementations of a transformation pipeline. | Reproducible benchmark report with plans and metrics. | Not Started
13 | Month 4 | Advanced PySpark patterns | Arrays/maps/structs; explode; nested JSON; UDF vs Pandas UDF vs built-ins; dates/timezones; reusable transformations/config. | PySpark API reference. Flatten nested API payloads and compare built-in expression to UDF. | API-to-lakehouse prototype parsing nested JSON and producing curated Parquet. | Modular pipeline with configuration, logging and quality checks. | Not Started
14 | Month 4 | Databricks workspace and notebooks | Workspace, notebooks, compute; Python/PySpark/SQL; files/volumes/catalog-schema-table; parameters/widgets; Git folders; Unity Catalog intro. | Databricks Python guide and DataFrame tutorial; use Free Edition subject to current limits. | Databricks onboarding notebook reading, validating, transforming and writing a table. | Parameterized notebook with execution statistics. | Not Started
15 | Month 4 | Delta Lake fundamentals | Delta transaction log; ACID; MERGE; inserts/updates/deletes; schema enforcement/evolution; time travel/history/restore; managed/external tables. | Delta Lake docs. Create a Delta table, modify rows, inspect history and test time travel where supported. | Incremental customer master with inserts, updates and deletes. | Idempotent upsert pipeline with reconciliation. | Not Started
16 | Month 4 | Lakehouse and medallion architecture | Bronze/Silver/Gold; raw vs clean vs aggregate; lineage; quality; Unity Catalog objects/permissions; dimensional modeling. | Databricks medallion architecture docs. Design e-commerce layers. | Three-layer pipeline for orders, customers and products. | Three Delta layers, documented transformations and quality results. | Not Started
17 | Month 5 | Incremental processing and CDC | Full vs incremental loads; watermarks; CDC; insert/update/delete; idempotency; retries; late-arriving records; deduplication. | Databricks ETL/CDC tutorials. Simulate daily extracts and rerun same batch. | Incremental customer/order pipeline with batch status and audit records. | Restartable incremental pipeline with duplicate protection. | Not Started
18 | Month 5 | Advanced performance optimization | AQE; broadcast joins; skew mitigation; shuffle reduction; file sizes; pruning; pushdown; compaction; data skipping; OPTIMIZE/clustering where supported. | Databricks optimization docs. Benchmark baseline vs optimized workload. | Optimize slow sales pipeline and document bottlenecks. | Report with runtime, shuffle/file metrics and rationale. | Not Started
19 | Month 5 | Structured Streaming | Batch vs streaming; micro-batches; sources/sinks; checkpoints; event time; watermarks; late events; deduplication; streaming to Delta. | Spark Structured Streaming guide. Simulate events via small files and test restart. | Near-real-time transaction monitoring with time-window aggregates. | Streaming notebook with checkpointing and recovery notes. | Not Started
20 | Month 5 | Workflow orchestration and operations | Databricks Jobs; task dependencies; parameters; schedules; retries/timeouts; alerts; run history; configuration; secrets; recovery. | Databricks Jobs docs. Split pipeline into ingestion, transform and aggregation tasks. | Scheduled ETL workflow with dependencies and failure handling. | Runnable workflow, execution log and rerun-safety evidence. | Not Started
21 | Month 6 | Data quality, testing and governance | Null/unique/referential/business checks; unit/integration tests; schema drift; data contracts; Unity Catalog privileges/lineage; PII; least privilege. | Unity Catalog docs. Introduce duplicates, missing keys, invalid dates; test failure paths. | Reusable data-quality framework with pass/fail, rejected records and reasons. | Tests and quality summary preventing silent bad data. | Not Started
22 | Month 6 | Deployment, reusable code and CI/CD | Python packages; Git branches/PRs; automated tests; Databricks Asset Bundles; environment variables; dev/test/prod separation. | Databricks Asset Bundles docs and GitHub Skills. Package notebook logic and configure deployment. | Deployable ETL package with reusable code, tests and job configuration. | Repository with deployment instructions and environment configuration. | Not Started
23 | Month 6 | Capstone design and ingestion | Requirements; source-target mapping; architecture; batch/incremental ingestion; layer design; contracts; audit columns; technical design. | Databricks learning resources. Choose retail/e-commerce/banking transactions dataset; design before coding. | Capstone architecture and working Bronze/Silver ingestion. | Architecture diagram, requirements, mapping and ingestion notebook. | Not Started
24 | Month 6 | Capstone business transformations | Joins/windows; deduplication; incremental MERGE; SCD Type 1/2; late data; Gold aggregations; source-target reconciliation. | Implement SCD Type 1 and 2; test duplicates, corrections, late and deleted records. | Customer dimension, transaction fact and Gold reporting tables. | Transformation pipeline with SCD, audit columns and reconciliation tests. | Not Started
25 | Month 6 | Capstone optimization and operations | Evidence-based tuning; quality gates; regression tests; scheduling/retries; idempotency; monitoring; runtime/counts/failures; cost awareness. | Benchmark capstone baseline; inject failures and verify recovery. | Production-readiness upgrade with tests, monitoring, recovery and optimization. | Measured benchmark and documented recovery procedure. | Not Started
26 | Month 6 | Final deployment and portfolio | Release docs; design trade-offs; Spark troubleshooting; code review; handover; interview practice; measured impact presentation. | Review official Databricks docs; mock interviews on Python, Pandas, PySpark, Spark internals and Delta Lake. | Publish portfolio-ready capstone with README, architecture, tests, benchmarks and deployment steps. | Complete project demo and repository. | Not Started

## Daily Tracker
Week | Month | Day | Suggested Session Focus | Detailed Task / Practice | Weekly Project Connection | Planned Hours | Planned Date | Actual Hours | Status | Evidence / Notes | GitHub Commit / Link
1 | Month 1 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Python basics and programming logic. Key topics: Variables; primitive data types; type conversion; operators; conditionals; loops; notebook/script execution. | ETL validation utility: validate employee IDs and salaries; separate valid and rejected records. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
1 | Month 1 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Python basics and programming logic. Key topics: Variables; primitive data types; type conversion; operators; conditionals; loops; notebook/script execution. | ETL validation utility: validate employee IDs and salaries; separate valid and rejected records. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
1 | Month 1 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Python basics and programming logic. Key topics: Variables; primitive data types; type conversion; operators; conditionals; loops; notebook/script execution. | ETL validation utility: validate employee IDs and salaries; separate valid and rejected records. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
1 | Month 1 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Python basics and programming logic. Key topics: Variables; primitive data types; type conversion; operators; conditionals; loops; notebook/script execution. | ETL validation utility: validate employee IDs and salaries; separate valid and rejected records. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
1 | Month 1 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Python basics and programming logic. Key topics: Variables; primitive data types; type conversion; operators; conditionals; loops; notebook/script execution. | ETL validation utility: validate employee IDs and salaries; separate valid and rejected records. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
1 | Month 1 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Python basics and programming logic. Key topics: Variables; primitive data types; type conversion; operators; conditionals; loops; notebook/script execution. | ETL validation utility: validate employee IDs and salaries; separate valid and rejected records. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
1 | Month 1 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Python basics and programming logic. Key topics: Variables; primitive data types; type conversion; operators; conditionals; loops; notebook/script execution. | ETL validation utility: validate employee IDs and salaries; separate valid and rejected records. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
2 | Month 1 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Data structures and functions. Key topics: Lists, tuples, sets, dictionaries; indexing/slicing; comprehensions; functions; parameters; return values; lambda; scope; nested JSON. | API response transformer: extract customers, calculate order totals, group orders, identify duplicate IDs. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
2 | Month 1 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Data structures and functions. Key topics: Lists, tuples, sets, dictionaries; indexing/slicing; comprehensions; functions; parameters; return values; lambda; scope; nested JSON. | API response transformer: extract customers, calculate order totals, group orders, identify duplicate IDs. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
2 | Month 1 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Data structures and functions. Key topics: Lists, tuples, sets, dictionaries; indexing/slicing; comprehensions; functions; parameters; return values; lambda; scope; nested JSON. | API response transformer: extract customers, calculate order totals, group orders, identify duplicate IDs. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
2 | Month 1 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Data structures and functions. Key topics: Lists, tuples, sets, dictionaries; indexing/slicing; comprehensions; functions; parameters; return values; lambda; scope; nested JSON. | API response transformer: extract customers, calculate order totals, group orders, identify duplicate IDs. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
2 | Month 1 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Data structures and functions. Key topics: Lists, tuples, sets, dictionaries; indexing/slicing; comprehensions; functions; parameters; return values; lambda; scope; nested JSON. | API response transformer: extract customers, calculate order totals, group orders, identify duplicate IDs. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
2 | Month 1 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Data structures and functions. Key topics: Lists, tuples, sets, dictionaries; indexing/slicing; comprehensions; functions; parameters; return values; lambda; scope; nested JSON. | API response transformer: extract customers, calculate order totals, group orders, identify duplicate IDs. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
2 | Month 1 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Data structures and functions. Key topics: Lists, tuples, sets, dictionaries; indexing/slicing; comprehensions; functions; parameters; return values; lambda; scope; nested JSON. | API response transformer: extract customers, calculate order totals, group orders, identify duplicate IDs. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
3 | Month 1 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Files, exceptions and reusable code. Key topics: CSV/JSON/text files; exceptions; logging; modules/packages; virtual environments; type hints; docstrings; OOP basics. | File-based ETL framework: read CSVs, validate schemas, consolidate outputs, quarantine rejects. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
3 | Month 1 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Files, exceptions and reusable code. Key topics: CSV/JSON/text files; exceptions; logging; modules/packages; virtual environments; type hints; docstrings; OOP basics. | File-based ETL framework: read CSVs, validate schemas, consolidate outputs, quarantine rejects. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
3 | Month 1 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Files, exceptions and reusable code. Key topics: CSV/JSON/text files; exceptions; logging; modules/packages; virtual environments; type hints; docstrings; OOP basics. | File-based ETL framework: read CSVs, validate schemas, consolidate outputs, quarantine rejects. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
3 | Month 1 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Files, exceptions and reusable code. Key topics: CSV/JSON/text files; exceptions; logging; modules/packages; virtual environments; type hints; docstrings; OOP basics. | File-based ETL framework: read CSVs, validate schemas, consolidate outputs, quarantine rejects. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
3 | Month 1 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Files, exceptions and reusable code. Key topics: CSV/JSON/text files; exceptions; logging; modules/packages; virtual environments; type hints; docstrings; OOP basics. | File-based ETL framework: read CSVs, validate schemas, consolidate outputs, quarantine rejects. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
3 | Month 1 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Files, exceptions and reusable code. Key topics: CSV/JSON/text files; exceptions; logging; modules/packages; virtual environments; type hints; docstrings; OOP basics. | File-based ETL framework: read CSVs, validate schemas, consolidate outputs, quarantine rejects. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
3 | Month 1 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Files, exceptions and reusable code. Key topics: CSV/JSON/text files; exceptions; logging; modules/packages; virtual environments; type hints; docstrings; OOP basics. | File-based ETL framework: read CSVs, validate schemas, consolidate outputs, quarantine rejects. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
4 | Month 1 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Advanced Python fundamentals and testing. Key topics: Iterators/generators; decorators; context managers; shallow/deep copy; pytest; mocking basics; Git basics. | Production-style CSV processing package split into ingestion, validation, transformation, logging and config. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
4 | Month 1 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Advanced Python fundamentals and testing. Key topics: Iterators/generators; decorators; context managers; shallow/deep copy; pytest; mocking basics; Git basics. | Production-style CSV processing package split into ingestion, validation, transformation, logging and config. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
4 | Month 1 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Advanced Python fundamentals and testing. Key topics: Iterators/generators; decorators; context managers; shallow/deep copy; pytest; mocking basics; Git basics. | Production-style CSV processing package split into ingestion, validation, transformation, logging and config. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
4 | Month 1 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Advanced Python fundamentals and testing. Key topics: Iterators/generators; decorators; context managers; shallow/deep copy; pytest; mocking basics; Git basics. | Production-style CSV processing package split into ingestion, validation, transformation, logging and config. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
4 | Month 1 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Advanced Python fundamentals and testing. Key topics: Iterators/generators; decorators; context managers; shallow/deep copy; pytest; mocking basics; Git basics. | Production-style CSV processing package split into ingestion, validation, transformation, logging and config. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
4 | Month 1 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Advanced Python fundamentals and testing. Key topics: Iterators/generators; decorators; context managers; shallow/deep copy; pytest; mocking basics; Git basics. | Production-style CSV processing package split into ingestion, validation, transformation, logging and config. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
4 | Month 1 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Advanced Python fundamentals and testing. Key topics: Iterators/generators; decorators; context managers; shallow/deep copy; pytest; mocking basics; Git basics. | Production-style CSV processing package split into ingestion, validation, transformation, logging and config. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
5 | Month 2 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: NumPy fundamentals. Key topics: ndarray; shape/dimensions; indexing; reshaping; broadcasting; vectorization; Boolean masks; aggregations; statistics. | Transaction analytics engine for revenue, averages, outliers, percentiles and category summaries. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
5 | Month 2 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: NumPy fundamentals. Key topics: ndarray; shape/dimensions; indexing; reshaping; broadcasting; vectorization; Boolean masks; aggregations; statistics. | Transaction analytics engine for revenue, averages, outliers, percentiles and category summaries. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
5 | Month 2 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: NumPy fundamentals. Key topics: ndarray; shape/dimensions; indexing; reshaping; broadcasting; vectorization; Boolean masks; aggregations; statistics. | Transaction analytics engine for revenue, averages, outliers, percentiles and category summaries. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
5 | Month 2 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: NumPy fundamentals. Key topics: ndarray; shape/dimensions; indexing; reshaping; broadcasting; vectorization; Boolean masks; aggregations; statistics. | Transaction analytics engine for revenue, averages, outliers, percentiles and category summaries. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
5 | Month 2 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: NumPy fundamentals. Key topics: ndarray; shape/dimensions; indexing; reshaping; broadcasting; vectorization; Boolean masks; aggregations; statistics. | Transaction analytics engine for revenue, averages, outliers, percentiles and category summaries. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
5 | Month 2 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: NumPy fundamentals. Key topics: ndarray; shape/dimensions; indexing; reshaping; broadcasting; vectorization; Boolean masks; aggregations; statistics. | Transaction analytics engine for revenue, averages, outliers, percentiles and category summaries. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
5 | Month 2 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: NumPy fundamentals. Key topics: ndarray; shape/dimensions; indexing; reshaping; broadcasting; vectorization; Boolean masks; aggregations; statistics. | Transaction analytics engine for revenue, averages, outliers, percentiles and category summaries. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
6 | Month 2 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Pandas DataFrames and data cleaning. Key topics: Series/DataFrame/index; CSV/JSON/Excel/Parquet I/O; filtering; sorting; missing values; duplicates; data types; schema checks. | Customer data cleansing pipeline standardizing names/emails, handling nulls and duplicates. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
6 | Month 2 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Pandas DataFrames and data cleaning. Key topics: Series/DataFrame/index; CSV/JSON/Excel/Parquet I/O; filtering; sorting; missing values; duplicates; data types; schema checks. | Customer data cleansing pipeline standardizing names/emails, handling nulls and duplicates. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
6 | Month 2 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Pandas DataFrames and data cleaning. Key topics: Series/DataFrame/index; CSV/JSON/Excel/Parquet I/O; filtering; sorting; missing values; duplicates; data types; schema checks. | Customer data cleansing pipeline standardizing names/emails, handling nulls and duplicates. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
6 | Month 2 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Pandas DataFrames and data cleaning. Key topics: Series/DataFrame/index; CSV/JSON/Excel/Parquet I/O; filtering; sorting; missing values; duplicates; data types; schema checks. | Customer data cleansing pipeline standardizing names/emails, handling nulls and duplicates. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
6 | Month 2 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Pandas DataFrames and data cleaning. Key topics: Series/DataFrame/index; CSV/JSON/Excel/Parquet I/O; filtering; sorting; missing values; duplicates; data types; schema checks. | Customer data cleansing pipeline standardizing names/emails, handling nulls and duplicates. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
6 | Month 2 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Pandas DataFrames and data cleaning. Key topics: Series/DataFrame/index; CSV/JSON/Excel/Parquet I/O; filtering; sorting; missing values; duplicates; data types; schema checks. | Customer data cleansing pipeline standardizing names/emails, handling nulls and duplicates. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
6 | Month 2 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Pandas DataFrames and data cleaning. Key topics: Series/DataFrame/index; CSV/JSON/Excel/Parquet I/O; filtering; sorting; missing values; duplicates; data types; schema checks. | Customer data cleansing pipeline standardizing names/emails, handling nulls and duplicates. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
7 | Month 2 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Advanced Pandas transformations. Key topics: groupby/agg/transform/apply; merge/join/concat; pivot/melt; dates; resampling; rolling windows; vectorized strings. | Sales/customer analytics: join orders/customers/products; monthly revenue, repeat purchases, top products, lifetime spend. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
7 | Month 2 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Advanced Pandas transformations. Key topics: groupby/agg/transform/apply; merge/join/concat; pivot/melt; dates; resampling; rolling windows; vectorized strings. | Sales/customer analytics: join orders/customers/products; monthly revenue, repeat purchases, top products, lifetime spend. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
7 | Month 2 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Advanced Pandas transformations. Key topics: groupby/agg/transform/apply; merge/join/concat; pivot/melt; dates; resampling; rolling windows; vectorized strings. | Sales/customer analytics: join orders/customers/products; monthly revenue, repeat purchases, top products, lifetime spend. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
7 | Month 2 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Advanced Pandas transformations. Key topics: groupby/agg/transform/apply; merge/join/concat; pivot/melt; dates; resampling; rolling windows; vectorized strings. | Sales/customer analytics: join orders/customers/products; monthly revenue, repeat purchases, top products, lifetime spend. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
7 | Month 2 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Advanced Pandas transformations. Key topics: groupby/agg/transform/apply; merge/join/concat; pivot/melt; dates; resampling; rolling windows; vectorized strings. | Sales/customer analytics: join orders/customers/products; monthly revenue, repeat purchases, top products, lifetime spend. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
7 | Month 2 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Advanced Pandas transformations. Key topics: groupby/agg/transform/apply; merge/join/concat; pivot/melt; dates; resampling; rolling windows; vectorized strings. | Sales/customer analytics: join orders/customers/products; monthly revenue, repeat purchases, top products, lifetime spend. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
7 | Month 2 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Advanced Pandas transformations. Key topics: groupby/agg/transform/apply; merge/join/concat; pivot/melt; dates; resampling; rolling windows; vectorized strings. | Sales/customer analytics: join orders/customers/products; monthly revenue, repeat purchases, top products, lifetime spend. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
8 | Month 2 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Pandas performance and data analysis. Key topics: Memory usage; efficient dtypes; chunked CSV; profiling; plotting; distributions; correlations; outliers; Pandas vs Spark. | Local data profiler reporting schema, nulls, duplicates, summaries and processing duration. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
8 | Month 2 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Pandas performance and data analysis. Key topics: Memory usage; efficient dtypes; chunked CSV; profiling; plotting; distributions; correlations; outliers; Pandas vs Spark. | Local data profiler reporting schema, nulls, duplicates, summaries and processing duration. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
8 | Month 2 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Pandas performance and data analysis. Key topics: Memory usage; efficient dtypes; chunked CSV; profiling; plotting; distributions; correlations; outliers; Pandas vs Spark. | Local data profiler reporting schema, nulls, duplicates, summaries and processing duration. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
8 | Month 2 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Pandas performance and data analysis. Key topics: Memory usage; efficient dtypes; chunked CSV; profiling; plotting; distributions; correlations; outliers; Pandas vs Spark. | Local data profiler reporting schema, nulls, duplicates, summaries and processing duration. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
8 | Month 2 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Pandas performance and data analysis. Key topics: Memory usage; efficient dtypes; chunked CSV; profiling; plotting; distributions; correlations; outliers; Pandas vs Spark. | Local data profiler reporting schema, nulls, duplicates, summaries and processing duration. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
8 | Month 2 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Pandas performance and data analysis. Key topics: Memory usage; efficient dtypes; chunked CSV; profiling; plotting; distributions; correlations; outliers; Pandas vs Spark. | Local data profiler reporting schema, nulls, duplicates, summaries and processing duration. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
8 | Month 2 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Pandas performance and data analysis. Key topics: Memory usage; efficient dtypes; chunked CSV; profiling; plotting; distributions; correlations; outliers; Pandas vs Spark. | Local data profiler reporting schema, nulls, duplicates, summaries and processing duration. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
9 | Month 3 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Spark architecture and PySpark setup. Key topics: Distributed computing; driver/executors; partitions/tasks; SparkSession; lazy evaluation; transformations/actions; schemas; CSV/JSON/Parquet. | First distributed ingestion pipeline with schema, filters and Parquet output. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
9 | Month 3 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Spark architecture and PySpark setup. Key topics: Distributed computing; driver/executors; partitions/tasks; SparkSession; lazy evaluation; transformations/actions; schemas; CSV/JSON/Parquet. | First distributed ingestion pipeline with schema, filters and Parquet output. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
9 | Month 3 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Spark architecture and PySpark setup. Key topics: Distributed computing; driver/executors; partitions/tasks; SparkSession; lazy evaluation; transformations/actions; schemas; CSV/JSON/Parquet. | First distributed ingestion pipeline with schema, filters and Parquet output. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
9 | Month 3 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Spark architecture and PySpark setup. Key topics: Distributed computing; driver/executors; partitions/tasks; SparkSession; lazy evaluation; transformations/actions; schemas; CSV/JSON/Parquet. | First distributed ingestion pipeline with schema, filters and Parquet output. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
9 | Month 3 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Spark architecture and PySpark setup. Key topics: Distributed computing; driver/executors; partitions/tasks; SparkSession; lazy evaluation; transformations/actions; schemas; CSV/JSON/Parquet. | First distributed ingestion pipeline with schema, filters and Parquet output. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
9 | Month 3 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Spark architecture and PySpark setup. Key topics: Distributed computing; driver/executors; partitions/tasks; SparkSession; lazy evaluation; transformations/actions; schemas; CSV/JSON/Parquet. | First distributed ingestion pipeline with schema, filters and Parquet output. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
9 | Month 3 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Spark architecture and PySpark setup. Key topics: Distributed computing; driver/executors; partitions/tasks; SparkSession; lazy evaluation; transformations/actions; schemas; CSV/JSON/Parquet. | First distributed ingestion pipeline with schema, filters and Parquet output. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
10 | Month 3 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: PySpark DataFrame transformations. Key topics: select/filter/withColumn/when; casts; null handling; deduplication; built-in functions; expressions; schema enforcement. | Transaction cleansing: standardized schema, quarantined invalid rows and rejection reasons. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
10 | Month 3 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: PySpark DataFrame transformations. Key topics: select/filter/withColumn/when; casts; null handling; deduplication; built-in functions; expressions; schema enforcement. | Transaction cleansing: standardized schema, quarantined invalid rows and rejection reasons. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
10 | Month 3 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: PySpark DataFrame transformations. Key topics: select/filter/withColumn/when; casts; null handling; deduplication; built-in functions; expressions; schema enforcement. | Transaction cleansing: standardized schema, quarantined invalid rows and rejection reasons. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
10 | Month 3 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: PySpark DataFrame transformations. Key topics: select/filter/withColumn/when; casts; null handling; deduplication; built-in functions; expressions; schema enforcement. | Transaction cleansing: standardized schema, quarantined invalid rows and rejection reasons. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
10 | Month 3 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: PySpark DataFrame transformations. Key topics: select/filter/withColumn/when; casts; null handling; deduplication; built-in functions; expressions; schema enforcement. | Transaction cleansing: standardized schema, quarantined invalid rows and rejection reasons. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
10 | Month 3 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: PySpark DataFrame transformations. Key topics: select/filter/withColumn/when; casts; null handling; deduplication; built-in functions; expressions; schema enforcement. | Transaction cleansing: standardized schema, quarantined invalid rows and rejection reasons. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
10 | Month 3 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: PySpark DataFrame transformations. Key topics: select/filter/withColumn/when; casts; null handling; deduplication; built-in functions; expressions; schema enforcement. | Transaction cleansing: standardized schema, quarantined invalid rows and rejection reasons. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
11 | Month 3 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Joins, aggregations and windows. Key topics: Inner/left/right/full/semi/anti joins; groupBy/agg; window specs; row_number/rank/dense_rank/lag/lead; business-key deduplication. | Customer 360 with lifetime spend, latest purchase, top products and transaction rankings. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
11 | Month 3 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Joins, aggregations and windows. Key topics: Inner/left/right/full/semi/anti joins; groupBy/agg; window specs; row_number/rank/dense_rank/lag/lead; business-key deduplication. | Customer 360 with lifetime spend, latest purchase, top products and transaction rankings. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
11 | Month 3 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Joins, aggregations and windows. Key topics: Inner/left/right/full/semi/anti joins; groupBy/agg; window specs; row_number/rank/dense_rank/lag/lead; business-key deduplication. | Customer 360 with lifetime spend, latest purchase, top products and transaction rankings. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
11 | Month 3 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Joins, aggregations and windows. Key topics: Inner/left/right/full/semi/anti joins; groupBy/agg; window specs; row_number/rank/dense_rank/lag/lead; business-key deduplication. | Customer 360 with lifetime spend, latest purchase, top products and transaction rankings. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
11 | Month 3 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Joins, aggregations and windows. Key topics: Inner/left/right/full/semi/anti joins; groupBy/agg; window specs; row_number/rank/dense_rank/lag/lead; business-key deduplication. | Customer 360 with lifetime spend, latest purchase, top products and transaction rankings. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
11 | Month 3 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Joins, aggregations and windows. Key topics: Inner/left/right/full/semi/anti joins; groupBy/agg; window specs; row_number/rank/dense_rank/lag/lead; business-key deduplication. | Customer 360 with lifetime spend, latest purchase, top products and transaction rankings. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
11 | Month 3 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Joins, aggregations and windows. Key topics: Inner/left/right/full/semi/anti joins; groupBy/agg; window specs; row_number/rank/dense_rank/lag/lead; business-key deduplication. | Customer 360 with lifetime spend, latest purchase, top products and transaction rankings. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
12 | Month 3 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Spark internals and performance. Key topics: Narrow/wide transformations; shuffles; jobs/stages/tasks; explain/physical plans; Spark UI; repartition/coalesce; broadcast; cache; skew. | Performance lab comparing 2–3 implementations of a transformation pipeline. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
12 | Month 3 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Spark internals and performance. Key topics: Narrow/wide transformations; shuffles; jobs/stages/tasks; explain/physical plans; Spark UI; repartition/coalesce; broadcast; cache; skew. | Performance lab comparing 2–3 implementations of a transformation pipeline. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
12 | Month 3 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Spark internals and performance. Key topics: Narrow/wide transformations; shuffles; jobs/stages/tasks; explain/physical plans; Spark UI; repartition/coalesce; broadcast; cache; skew. | Performance lab comparing 2–3 implementations of a transformation pipeline. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
12 | Month 3 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Spark internals and performance. Key topics: Narrow/wide transformations; shuffles; jobs/stages/tasks; explain/physical plans; Spark UI; repartition/coalesce; broadcast; cache; skew. | Performance lab comparing 2–3 implementations of a transformation pipeline. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
12 | Month 3 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Spark internals and performance. Key topics: Narrow/wide transformations; shuffles; jobs/stages/tasks; explain/physical plans; Spark UI; repartition/coalesce; broadcast; cache; skew. | Performance lab comparing 2–3 implementations of a transformation pipeline. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
12 | Month 3 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Spark internals and performance. Key topics: Narrow/wide transformations; shuffles; jobs/stages/tasks; explain/physical plans; Spark UI; repartition/coalesce; broadcast; cache; skew. | Performance lab comparing 2–3 implementations of a transformation pipeline. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
12 | Month 3 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Spark internals and performance. Key topics: Narrow/wide transformations; shuffles; jobs/stages/tasks; explain/physical plans; Spark UI; repartition/coalesce; broadcast; cache; skew. | Performance lab comparing 2–3 implementations of a transformation pipeline. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
13 | Month 4 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Advanced PySpark patterns. Key topics: Arrays/maps/structs; explode; nested JSON; UDF vs Pandas UDF vs built-ins; dates/timezones; reusable transformations/config. | API-to-lakehouse prototype parsing nested JSON and producing curated Parquet. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
13 | Month 4 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Advanced PySpark patterns. Key topics: Arrays/maps/structs; explode; nested JSON; UDF vs Pandas UDF vs built-ins; dates/timezones; reusable transformations/config. | API-to-lakehouse prototype parsing nested JSON and producing curated Parquet. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
13 | Month 4 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Advanced PySpark patterns. Key topics: Arrays/maps/structs; explode; nested JSON; UDF vs Pandas UDF vs built-ins; dates/timezones; reusable transformations/config. | API-to-lakehouse prototype parsing nested JSON and producing curated Parquet. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
13 | Month 4 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Advanced PySpark patterns. Key topics: Arrays/maps/structs; explode; nested JSON; UDF vs Pandas UDF vs built-ins; dates/timezones; reusable transformations/config. | API-to-lakehouse prototype parsing nested JSON and producing curated Parquet. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
13 | Month 4 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Advanced PySpark patterns. Key topics: Arrays/maps/structs; explode; nested JSON; UDF vs Pandas UDF vs built-ins; dates/timezones; reusable transformations/config. | API-to-lakehouse prototype parsing nested JSON and producing curated Parquet. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
13 | Month 4 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Advanced PySpark patterns. Key topics: Arrays/maps/structs; explode; nested JSON; UDF vs Pandas UDF vs built-ins; dates/timezones; reusable transformations/config. | API-to-lakehouse prototype parsing nested JSON and producing curated Parquet. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
13 | Month 4 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Advanced PySpark patterns. Key topics: Arrays/maps/structs; explode; nested JSON; UDF vs Pandas UDF vs built-ins; dates/timezones; reusable transformations/config. | API-to-lakehouse prototype parsing nested JSON and producing curated Parquet. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
14 | Month 4 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Databricks workspace and notebooks. Key topics: Workspace, notebooks, compute; Python/PySpark/SQL; files/volumes/catalog-schema-table; parameters/widgets; Git folders; Unity Catalog intro. | Databricks onboarding notebook reading, validating, transforming and writing a table. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
14 | Month 4 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Databricks workspace and notebooks. Key topics: Workspace, notebooks, compute; Python/PySpark/SQL; files/volumes/catalog-schema-table; parameters/widgets; Git folders; Unity Catalog intro. | Databricks onboarding notebook reading, validating, transforming and writing a table. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
14 | Month 4 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Databricks workspace and notebooks. Key topics: Workspace, notebooks, compute; Python/PySpark/SQL; files/volumes/catalog-schema-table; parameters/widgets; Git folders; Unity Catalog intro. | Databricks onboarding notebook reading, validating, transforming and writing a table. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
14 | Month 4 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Databricks workspace and notebooks. Key topics: Workspace, notebooks, compute; Python/PySpark/SQL; files/volumes/catalog-schema-table; parameters/widgets; Git folders; Unity Catalog intro. | Databricks onboarding notebook reading, validating, transforming and writing a table. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
14 | Month 4 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Databricks workspace and notebooks. Key topics: Workspace, notebooks, compute; Python/PySpark/SQL; files/volumes/catalog-schema-table; parameters/widgets; Git folders; Unity Catalog intro. | Databricks onboarding notebook reading, validating, transforming and writing a table. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
14 | Month 4 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Databricks workspace and notebooks. Key topics: Workspace, notebooks, compute; Python/PySpark/SQL; files/volumes/catalog-schema-table; parameters/widgets; Git folders; Unity Catalog intro. | Databricks onboarding notebook reading, validating, transforming and writing a table. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
14 | Month 4 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Databricks workspace and notebooks. Key topics: Workspace, notebooks, compute; Python/PySpark/SQL; files/volumes/catalog-schema-table; parameters/widgets; Git folders; Unity Catalog intro. | Databricks onboarding notebook reading, validating, transforming and writing a table. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
15 | Month 4 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Delta Lake fundamentals. Key topics: Delta transaction log; ACID; MERGE; inserts/updates/deletes; schema enforcement/evolution; time travel/history/restore; managed/external tables. | Incremental customer master with inserts, updates and deletes. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
15 | Month 4 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Delta Lake fundamentals. Key topics: Delta transaction log; ACID; MERGE; inserts/updates/deletes; schema enforcement/evolution; time travel/history/restore; managed/external tables. | Incremental customer master with inserts, updates and deletes. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
15 | Month 4 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Delta Lake fundamentals. Key topics: Delta transaction log; ACID; MERGE; inserts/updates/deletes; schema enforcement/evolution; time travel/history/restore; managed/external tables. | Incremental customer master with inserts, updates and deletes. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
15 | Month 4 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Delta Lake fundamentals. Key topics: Delta transaction log; ACID; MERGE; inserts/updates/deletes; schema enforcement/evolution; time travel/history/restore; managed/external tables. | Incremental customer master with inserts, updates and deletes. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
15 | Month 4 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Delta Lake fundamentals. Key topics: Delta transaction log; ACID; MERGE; inserts/updates/deletes; schema enforcement/evolution; time travel/history/restore; managed/external tables. | Incremental customer master with inserts, updates and deletes. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
15 | Month 4 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Delta Lake fundamentals. Key topics: Delta transaction log; ACID; MERGE; inserts/updates/deletes; schema enforcement/evolution; time travel/history/restore; managed/external tables. | Incremental customer master with inserts, updates and deletes. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
15 | Month 4 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Delta Lake fundamentals. Key topics: Delta transaction log; ACID; MERGE; inserts/updates/deletes; schema enforcement/evolution; time travel/history/restore; managed/external tables. | Incremental customer master with inserts, updates and deletes. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
16 | Month 4 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Lakehouse and medallion architecture. Key topics: Bronze/Silver/Gold; raw vs clean vs aggregate; lineage; quality; Unity Catalog objects/permissions; dimensional modeling. | Three-layer pipeline for orders, customers and products. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
16 | Month 4 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Lakehouse and medallion architecture. Key topics: Bronze/Silver/Gold; raw vs clean vs aggregate; lineage; quality; Unity Catalog objects/permissions; dimensional modeling. | Three-layer pipeline for orders, customers and products. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
16 | Month 4 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Lakehouse and medallion architecture. Key topics: Bronze/Silver/Gold; raw vs clean vs aggregate; lineage; quality; Unity Catalog objects/permissions; dimensional modeling. | Three-layer pipeline for orders, customers and products. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
16 | Month 4 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Lakehouse and medallion architecture. Key topics: Bronze/Silver/Gold; raw vs clean vs aggregate; lineage; quality; Unity Catalog objects/permissions; dimensional modeling. | Three-layer pipeline for orders, customers and products. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
16 | Month 4 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Lakehouse and medallion architecture. Key topics: Bronze/Silver/Gold; raw vs clean vs aggregate; lineage; quality; Unity Catalog objects/permissions; dimensional modeling. | Three-layer pipeline for orders, customers and products. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
16 | Month 4 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Lakehouse and medallion architecture. Key topics: Bronze/Silver/Gold; raw vs clean vs aggregate; lineage; quality; Unity Catalog objects/permissions; dimensional modeling. | Three-layer pipeline for orders, customers and products. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
16 | Month 4 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Lakehouse and medallion architecture. Key topics: Bronze/Silver/Gold; raw vs clean vs aggregate; lineage; quality; Unity Catalog objects/permissions; dimensional modeling. | Three-layer pipeline for orders, customers and products. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
17 | Month 5 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Incremental processing and CDC. Key topics: Full vs incremental loads; watermarks; CDC; insert/update/delete; idempotency; retries; late-arriving records; deduplication. | Incremental customer/order pipeline with batch status and audit records. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
17 | Month 5 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Incremental processing and CDC. Key topics: Full vs incremental loads; watermarks; CDC; insert/update/delete; idempotency; retries; late-arriving records; deduplication. | Incremental customer/order pipeline with batch status and audit records. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
17 | Month 5 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Incremental processing and CDC. Key topics: Full vs incremental loads; watermarks; CDC; insert/update/delete; idempotency; retries; late-arriving records; deduplication. | Incremental customer/order pipeline with batch status and audit records. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
17 | Month 5 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Incremental processing and CDC. Key topics: Full vs incremental loads; watermarks; CDC; insert/update/delete; idempotency; retries; late-arriving records; deduplication. | Incremental customer/order pipeline with batch status and audit records. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
17 | Month 5 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Incremental processing and CDC. Key topics: Full vs incremental loads; watermarks; CDC; insert/update/delete; idempotency; retries; late-arriving records; deduplication. | Incremental customer/order pipeline with batch status and audit records. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
17 | Month 5 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Incremental processing and CDC. Key topics: Full vs incremental loads; watermarks; CDC; insert/update/delete; idempotency; retries; late-arriving records; deduplication. | Incremental customer/order pipeline with batch status and audit records. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
17 | Month 5 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Incremental processing and CDC. Key topics: Full vs incremental loads; watermarks; CDC; insert/update/delete; idempotency; retries; late-arriving records; deduplication. | Incremental customer/order pipeline with batch status and audit records. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
18 | Month 5 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Advanced performance optimization. Key topics: AQE; broadcast joins; skew mitigation; shuffle reduction; file sizes; pruning; pushdown; compaction; data skipping; OPTIMIZE/clustering where supported. | Optimize slow sales pipeline and document bottlenecks. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
18 | Month 5 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Advanced performance optimization. Key topics: AQE; broadcast joins; skew mitigation; shuffle reduction; file sizes; pruning; pushdown; compaction; data skipping; OPTIMIZE/clustering where supported. | Optimize slow sales pipeline and document bottlenecks. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
18 | Month 5 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Advanced performance optimization. Key topics: AQE; broadcast joins; skew mitigation; shuffle reduction; file sizes; pruning; pushdown; compaction; data skipping; OPTIMIZE/clustering where supported. | Optimize slow sales pipeline and document bottlenecks. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
18 | Month 5 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Advanced performance optimization. Key topics: AQE; broadcast joins; skew mitigation; shuffle reduction; file sizes; pruning; pushdown; compaction; data skipping; OPTIMIZE/clustering where supported. | Optimize slow sales pipeline and document bottlenecks. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
18 | Month 5 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Advanced performance optimization. Key topics: AQE; broadcast joins; skew mitigation; shuffle reduction; file sizes; pruning; pushdown; compaction; data skipping; OPTIMIZE/clustering where supported. | Optimize slow sales pipeline and document bottlenecks. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
18 | Month 5 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Advanced performance optimization. Key topics: AQE; broadcast joins; skew mitigation; shuffle reduction; file sizes; pruning; pushdown; compaction; data skipping; OPTIMIZE/clustering where supported. | Optimize slow sales pipeline and document bottlenecks. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
18 | Month 5 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Advanced performance optimization. Key topics: AQE; broadcast joins; skew mitigation; shuffle reduction; file sizes; pruning; pushdown; compaction; data skipping; OPTIMIZE/clustering where supported. | Optimize slow sales pipeline and document bottlenecks. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
19 | Month 5 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Structured Streaming. Key topics: Batch vs streaming; micro-batches; sources/sinks; checkpoints; event time; watermarks; late events; deduplication; streaming to Delta. | Near-real-time transaction monitoring with time-window aggregates. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
19 | Month 5 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Structured Streaming. Key topics: Batch vs streaming; micro-batches; sources/sinks; checkpoints; event time; watermarks; late events; deduplication; streaming to Delta. | Near-real-time transaction monitoring with time-window aggregates. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
19 | Month 5 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Structured Streaming. Key topics: Batch vs streaming; micro-batches; sources/sinks; checkpoints; event time; watermarks; late events; deduplication; streaming to Delta. | Near-real-time transaction monitoring with time-window aggregates. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
19 | Month 5 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Structured Streaming. Key topics: Batch vs streaming; micro-batches; sources/sinks; checkpoints; event time; watermarks; late events; deduplication; streaming to Delta. | Near-real-time transaction monitoring with time-window aggregates. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
19 | Month 5 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Structured Streaming. Key topics: Batch vs streaming; micro-batches; sources/sinks; checkpoints; event time; watermarks; late events; deduplication; streaming to Delta. | Near-real-time transaction monitoring with time-window aggregates. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
19 | Month 5 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Structured Streaming. Key topics: Batch vs streaming; micro-batches; sources/sinks; checkpoints; event time; watermarks; late events; deduplication; streaming to Delta. | Near-real-time transaction monitoring with time-window aggregates. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
19 | Month 5 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Structured Streaming. Key topics: Batch vs streaming; micro-batches; sources/sinks; checkpoints; event time; watermarks; late events; deduplication; streaming to Delta. | Near-real-time transaction monitoring with time-window aggregates. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
20 | Month 5 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Workflow orchestration and operations. Key topics: Databricks Jobs; task dependencies; parameters; schedules; retries/timeouts; alerts; run history; configuration; secrets; recovery. | Scheduled ETL workflow with dependencies and failure handling. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
20 | Month 5 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Workflow orchestration and operations. Key topics: Databricks Jobs; task dependencies; parameters; schedules; retries/timeouts; alerts; run history; configuration; secrets; recovery. | Scheduled ETL workflow with dependencies and failure handling. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
20 | Month 5 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Workflow orchestration and operations. Key topics: Databricks Jobs; task dependencies; parameters; schedules; retries/timeouts; alerts; run history; configuration; secrets; recovery. | Scheduled ETL workflow with dependencies and failure handling. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
20 | Month 5 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Workflow orchestration and operations. Key topics: Databricks Jobs; task dependencies; parameters; schedules; retries/timeouts; alerts; run history; configuration; secrets; recovery. | Scheduled ETL workflow with dependencies and failure handling. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
20 | Month 5 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Workflow orchestration and operations. Key topics: Databricks Jobs; task dependencies; parameters; schedules; retries/timeouts; alerts; run history; configuration; secrets; recovery. | Scheduled ETL workflow with dependencies and failure handling. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
20 | Month 5 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Workflow orchestration and operations. Key topics: Databricks Jobs; task dependencies; parameters; schedules; retries/timeouts; alerts; run history; configuration; secrets; recovery. | Scheduled ETL workflow with dependencies and failure handling. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
20 | Month 5 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Workflow orchestration and operations. Key topics: Databricks Jobs; task dependencies; parameters; schedules; retries/timeouts; alerts; run history; configuration; secrets; recovery. | Scheduled ETL workflow with dependencies and failure handling. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
21 | Month 6 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Data quality, testing and governance. Key topics: Null/unique/referential/business checks; unit/integration tests; schema drift; data contracts; Unity Catalog privileges/lineage; PII; least privilege. | Reusable data-quality framework with pass/fail, rejected records and reasons. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
21 | Month 6 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Data quality, testing and governance. Key topics: Null/unique/referential/business checks; unit/integration tests; schema drift; data contracts; Unity Catalog privileges/lineage; PII; least privilege. | Reusable data-quality framework with pass/fail, rejected records and reasons. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
21 | Month 6 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Data quality, testing and governance. Key topics: Null/unique/referential/business checks; unit/integration tests; schema drift; data contracts; Unity Catalog privileges/lineage; PII; least privilege. | Reusable data-quality framework with pass/fail, rejected records and reasons. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
21 | Month 6 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Data quality, testing and governance. Key topics: Null/unique/referential/business checks; unit/integration tests; schema drift; data contracts; Unity Catalog privileges/lineage; PII; least privilege. | Reusable data-quality framework with pass/fail, rejected records and reasons. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
21 | Month 6 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Data quality, testing and governance. Key topics: Null/unique/referential/business checks; unit/integration tests; schema drift; data contracts; Unity Catalog privileges/lineage; PII; least privilege. | Reusable data-quality framework with pass/fail, rejected records and reasons. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
21 | Month 6 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Data quality, testing and governance. Key topics: Null/unique/referential/business checks; unit/integration tests; schema drift; data contracts; Unity Catalog privileges/lineage; PII; least privilege. | Reusable data-quality framework with pass/fail, rejected records and reasons. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
21 | Month 6 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Data quality, testing and governance. Key topics: Null/unique/referential/business checks; unit/integration tests; schema drift; data contracts; Unity Catalog privileges/lineage; PII; least privilege. | Reusable data-quality framework with pass/fail, rejected records and reasons. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
22 | Month 6 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Deployment, reusable code and CI/CD. Key topics: Python packages; Git branches/PRs; automated tests; Databricks Asset Bundles; environment variables; dev/test/prod separation. | Deployable ETL package with reusable code, tests and job configuration. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
22 | Month 6 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Deployment, reusable code and CI/CD. Key topics: Python packages; Git branches/PRs; automated tests; Databricks Asset Bundles; environment variables; dev/test/prod separation. | Deployable ETL package with reusable code, tests and job configuration. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
22 | Month 6 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Deployment, reusable code and CI/CD. Key topics: Python packages; Git branches/PRs; automated tests; Databricks Asset Bundles; environment variables; dev/test/prod separation. | Deployable ETL package with reusable code, tests and job configuration. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
22 | Month 6 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Deployment, reusable code and CI/CD. Key topics: Python packages; Git branches/PRs; automated tests; Databricks Asset Bundles; environment variables; dev/test/prod separation. | Deployable ETL package with reusable code, tests and job configuration. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
22 | Month 6 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Deployment, reusable code and CI/CD. Key topics: Python packages; Git branches/PRs; automated tests; Databricks Asset Bundles; environment variables; dev/test/prod separation. | Deployable ETL package with reusable code, tests and job configuration. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
22 | Month 6 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Deployment, reusable code and CI/CD. Key topics: Python packages; Git branches/PRs; automated tests; Databricks Asset Bundles; environment variables; dev/test/prod separation. | Deployable ETL package with reusable code, tests and job configuration. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
22 | Month 6 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Deployment, reusable code and CI/CD. Key topics: Python packages; Git branches/PRs; automated tests; Databricks Asset Bundles; environment variables; dev/test/prod separation. | Deployable ETL package with reusable code, tests and job configuration. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
23 | Month 6 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Capstone design and ingestion. Key topics: Requirements; source-target mapping; architecture; batch/incremental ingestion; layer design; contracts; audit columns; technical design. | Capstone architecture and working Bronze/Silver ingestion. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
23 | Month 6 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Capstone design and ingestion. Key topics: Requirements; source-target mapping; architecture; batch/incremental ingestion; layer design; contracts; audit columns; technical design. | Capstone architecture and working Bronze/Silver ingestion. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
23 | Month 6 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Capstone design and ingestion. Key topics: Requirements; source-target mapping; architecture; batch/incremental ingestion; layer design; contracts; audit columns; technical design. | Capstone architecture and working Bronze/Silver ingestion. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
23 | Month 6 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Capstone design and ingestion. Key topics: Requirements; source-target mapping; architecture; batch/incremental ingestion; layer design; contracts; audit columns; technical design. | Capstone architecture and working Bronze/Silver ingestion. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
23 | Month 6 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Capstone design and ingestion. Key topics: Requirements; source-target mapping; architecture; batch/incremental ingestion; layer design; contracts; audit columns; technical design. | Capstone architecture and working Bronze/Silver ingestion. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
23 | Month 6 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Capstone design and ingestion. Key topics: Requirements; source-target mapping; architecture; batch/incremental ingestion; layer design; contracts; audit columns; technical design. | Capstone architecture and working Bronze/Silver ingestion. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
23 | Month 6 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Capstone design and ingestion. Key topics: Requirements; source-target mapping; architecture; batch/incremental ingestion; layer design; contracts; audit columns; technical design. | Capstone architecture and working Bronze/Silver ingestion. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
24 | Month 6 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Capstone business transformations. Key topics: Joins/windows; deduplication; incremental MERGE; SCD Type 1/2; late data; Gold aggregations; source-target reconciliation. | Customer dimension, transaction fact and Gold reporting tables. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
24 | Month 6 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Capstone business transformations. Key topics: Joins/windows; deduplication; incremental MERGE; SCD Type 1/2; late data; Gold aggregations; source-target reconciliation. | Customer dimension, transaction fact and Gold reporting tables. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
24 | Month 6 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Capstone business transformations. Key topics: Joins/windows; deduplication; incremental MERGE; SCD Type 1/2; late data; Gold aggregations; source-target reconciliation. | Customer dimension, transaction fact and Gold reporting tables. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
24 | Month 6 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Capstone business transformations. Key topics: Joins/windows; deduplication; incremental MERGE; SCD Type 1/2; late data; Gold aggregations; source-target reconciliation. | Customer dimension, transaction fact and Gold reporting tables. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
24 | Month 6 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Capstone business transformations. Key topics: Joins/windows; deduplication; incremental MERGE; SCD Type 1/2; late data; Gold aggregations; source-target reconciliation. | Customer dimension, transaction fact and Gold reporting tables. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
24 | Month 6 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Capstone business transformations. Key topics: Joins/windows; deduplication; incremental MERGE; SCD Type 1/2; late data; Gold aggregations; source-target reconciliation. | Customer dimension, transaction fact and Gold reporting tables. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
24 | Month 6 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Capstone business transformations. Key topics: Joins/windows; deduplication; incremental MERGE; SCD Type 1/2; late data; Gold aggregations; source-target reconciliation. | Customer dimension, transaction fact and Gold reporting tables. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
25 | Month 6 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Capstone optimization and operations. Key topics: Evidence-based tuning; quality gates; regression tests; scheduling/retries; idempotency; monitoring; runtime/counts/failures; cost awareness. | Production-readiness upgrade with tests, monitoring, recovery and optimization. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
25 | Month 6 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Capstone optimization and operations. Key topics: Evidence-based tuning; quality gates; regression tests; scheduling/retries; idempotency; monitoring; runtime/counts/failures; cost awareness. | Production-readiness upgrade with tests, monitoring, recovery and optimization. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
25 | Month 6 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Capstone optimization and operations. Key topics: Evidence-based tuning; quality gates; regression tests; scheduling/retries; idempotency; monitoring; runtime/counts/failures; cost awareness. | Production-readiness upgrade with tests, monitoring, recovery and optimization. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
25 | Month 6 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Capstone optimization and operations. Key topics: Evidence-based tuning; quality gates; regression tests; scheduling/retries; idempotency; monitoring; runtime/counts/failures; cost awareness. | Production-readiness upgrade with tests, monitoring, recovery and optimization. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
25 | Month 6 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Capstone optimization and operations. Key topics: Evidence-based tuning; quality gates; regression tests; scheduling/retries; idempotency; monitoring; runtime/counts/failures; cost awareness. | Production-readiness upgrade with tests, monitoring, recovery and optimization. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
25 | Month 6 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Capstone optimization and operations. Key topics: Evidence-based tuning; quality gates; regression tests; scheduling/retries; idempotency; monitoring; runtime/counts/failures; cost awareness. | Production-readiness upgrade with tests, monitoring, recovery and optimization. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
25 | Month 6 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Capstone optimization and operations. Key topics: Evidence-based tuning; quality gates; regression tests; scheduling/retries; idempotency; monitoring; runtime/counts/failures; cost awareness. | Production-readiness upgrade with tests, monitoring, recovery and optimization. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started
26 | Month 6 | Day 1 | Learn core concepts | Read/watch the week’s core material and write concise notes. Focus on: Final deployment and portfolio. Key topics: Release docs; design trade-offs; Spark troubleshooting; code review; handover; interview practice; measured impact presentation. | Publish portfolio-ready capstone with README, architecture, tests, benchmarks and deployment steps. — session 1/7: scope and plan | 1.5 |  | 0 | Not Started
26 | Month 6 | Day 2 | Follow guided examples | Recreate 2–3 examples without copy-pasting; explain each step in your own words. Focus on: Final deployment and portfolio. Key topics: Release docs; design trade-offs; Spark troubleshooting; code review; handover; interview practice; measured impact presentation. | Publish portfolio-ready capstone with README, architecture, tests, benchmarks and deployment steps. — session 2/7: examples and setup | 1.5 |  | 0 | Not Started
26 | Month 6 | Day 3 | Focused exercises | Solve small exercises related to the week’s key concepts. Focus on: Final deployment and portfolio. Key topics: Release docs; design trade-offs; Spark troubleshooting; code review; handover; interview practice; measured impact presentation. | Publish portfolio-ready capstone with README, architecture, tests, benchmarks and deployment steps. — session 3/7: first implementation | 1.5 |  | 0 | Not Started
26 | Month 6 | Day 4 | Apply to realistic data | Use a sample dataset; implement transformations and inspect edge cases. Focus on: Final deployment and portfolio. Key topics: Release docs; design trade-offs; Spark troubleshooting; code review; handover; interview practice; measured impact presentation. | Publish portfolio-ready capstone with README, architecture, tests, benchmarks and deployment steps. — session 4/7: data transformation | 1.5 |  | 0 | Not Started
26 | Month 6 | Day 5 | Debug and deepen | Test nulls, duplicates, invalid input and edge cases; profile or inspect output where relevant. Focus on: Final deployment and portfolio. Key topics: Release docs; design trade-offs; Spark troubleshooting; code review; handover; interview practice; measured impact presentation. | Publish portfolio-ready capstone with README, architecture, tests, benchmarks and deployment steps. — session 5/7: edge cases and validation | 1.5 |  | 0 | Not Started
26 | Month 6 | Day 6 | Build mini-project | Implement the next part of the weekly mini-project and commit your work to Git. Focus on: Final deployment and portfolio. Key topics: Release docs; design trade-offs; Spark troubleshooting; code review; handover; interview practice; measured impact presentation. | Publish portfolio-ready capstone with README, architecture, tests, benchmarks and deployment steps. — session 6/7: implementation and integration | 1.5 |  | 0 | Not Started
26 | Month 6 | Day 7 | Review and deliver | Finish deliverable, validate results, write README/notes and record lessons learned. Focus on: Final deployment and portfolio. Key topics: Release docs; design trade-offs; Spark troubleshooting; code review; handover; interview practice; measured impact presentation. | Publish portfolio-ready capstone with README, architecture, tests, benchmarks and deployment steps. — session 7/7: final validation and documentation | 1 |  | 0 | Not Started

## Free Resources
Resource | URL | Relevant Weeks | How to Use It
Python official tutorial | https://docs.python.org/3/tutorial/ | Weeks 1–4 | Core language, data structures, functions, files and modules.
Python standard library | https://docs.python.org/3/library/ | Weeks 3–4 | CSV/JSON, logging, pathlib, testing utilities.
pytest documentation | https://docs.pytest.org/ | Weeks 4, 21–26 | Testing and test organization.
GitHub Skills | https://skills.github.com/ | Throughout | Git, GitHub workflows, repositories and collaboration.
NumPy beginner guide | https://numpy.org/doc/stable/user/absolute_beginners.html | Week 5 | Arrays, indexing, vectorization and aggregations.
Pandas getting started | https://pandas.pydata.org/docs/getting_started/ | Weeks 6–8 | DataFrame basics and common operations.
Pandas scaling guide | https://pandas.pydata.org/docs/user_guide/scale.html | Week 8 | Performance, memory and larger-than-memory data.
Pandas merging guide | https://pandas.pydata.org/docs/user_guide/merging.html | Week 7 | Joins and concatenation.
Pandas groupby guide | https://pandas.pydata.org/docs/user_guide/groupby.html | Week 7 | GroupBy and aggregation.
Apache Spark documentation | https://spark.apache.org/docs/latest/ | Weeks 9–13, 18–19 | Spark fundamentals and APIs.
Spark SQL and DataFrames | https://spark.apache.org/docs/latest/sql-programming-guide.html | Weeks 9–13 | DataFrame API and SQL.
Spark performance tuning | https://spark.apache.org/docs/latest/sql-performance-tuning.html | Weeks 12, 18, 25 | Joins, AQE and optimization.
PySpark window API | https://spark.apache.org/docs/latest/api/python/reference/pyspark.sql/window.html | Week 11 | Window specifications.
Structured Streaming | https://spark.apache.org/docs/latest/streaming/index.html | Week 19 | Streaming, checkpoints and event-time processing.
Databricks Free Edition | https://www.databricks.com/learn/free-edition | Weeks 9–26 | Hands-on platform practice; check current limits.
Databricks Python guide | https://docs.databricks.com/aws/en/languages/python | Weeks 14–26 | Python and notebook use in Databricks.
Databricks DataFrame tutorial | https://docs.databricks.com/aws/en/getting-started/dataframes | Week 14 | Getting started with DataFrames.
Delta Lake documentation | https://docs.delta.io/latest/index.html | Weeks 15–17 | Delta tables and transaction capabilities.
Medallion architecture | https://docs.databricks.com/aws/en/lakehouse/medallion | Week 16 and capstone | Bronze/Silver/Gold architecture.
Databricks optimization | https://docs.databricks.com/aws/en/optimizations | Weeks 18, 25 | Platform performance optimization.
Databricks Jobs | https://docs.databricks.com/aws/en/jobs/ | Week 20 | Workflow orchestration and operations.
Unity Catalog | https://docs.databricks.com/aws/en/data-governance/unity-catalog | Week 21 | Governance, permissions and lineage.
Databricks Asset Bundles | https://docs.databricks.com/aws/en/dev-tools/bundles/ | Week 22 | Deployment and CI/CD foundations.
Kaggle datasets | https://www.kaggle.com/datasets | Weeks 6 onward | Public practice datasets.
Google Colab | https://colab.research.google.com/ | Weeks 1–8 | Browser-based Python notebooks.

## GitHub Setup Guide
Create GitHub repository: databricks-data-engineering-journey
Step | Action | Details / Example | Done?
1 | Create/sign in to GitHub | Open https://github.com/ and sign in, or create an account. Enable two-factor authentication if possible. | Not Started
2 | Create a new repository | Click the + menu (top-right) → New repository. Repository name: databricks-data-engineering-journey. | Not Started
3 | Choose visibility | Choose Public if you want a portfolio, or Private while learning. Never upload company/client data, credentials, tokens, or proprietary code. | Not Started
4 | Initialize repository | Add a README. Optionally add a Python .gitignore and choose a license only if you understand how you want others to reuse your work. | Not Started
5 | Create repository | Click Create repository. Copy the repository URL shown by GitHub, e.g. https://github.com/YOUR-USERNAME/databricks-data-engineering-journey.git. | Not Started
6 | Install Git (if using a computer) | Install Git from https://git-scm.com/downloads. Configure your name/email in a terminal: git config --global user.name "Your Name" and git config --global user.email "you@example.com". | Not Started
7 | Clone the repository | In terminal: git clone https://github.com/YOUR-USERNAME/databricks-data-engineering-journey.git ; then cd databricks-data-engineering-journey. Replace YOUR-USERNAME. | Not Started
8 | Create a useful folder structure | Create folders: python-foundations/, numpy-pandas/, pyspark/, databricks/, capstone/, notes/. Add a README.md in each substantial project folder. | Not Started
9 | Add starter files | Create README.md, .gitignore, requirements.txt (or pyproject.toml later), and a projects/README.md. Keep sample data small and non-sensitive. | Not Started
10 | Make your first commit | Run: git add . ; git commit -m "Set up learning journey repository" ; git push origin main. If Git asks you to authenticate, follow GitHub's current authentication instructions. | Not Started
11 | Use a weekly workflow | Before a new topic: git pull. Work on a small branch if appropriate, test your code, then commit with a clear message such as "Add week 01 ETL validation utility" and push. | Not Started
12 | Link evidence to tracker | Paste the GitHub folder, commit or notebook link into the Daily Tracker's GitHub Commit / Link column. Update each weekly deliverable in the roadmap. | Not Started
13 | Use Databricks with Git | If your Databricks workspace supports Git folders, connect the repository using its Git integration and follow the workspace's authentication/policy requirements. Otherwise develop locally and push code to GitHub. | Not Started
14 | Publish your capstone | Include architecture diagram, setup instructions, synthetic/public sample data instructions, tests, screenshots that contain no sensitive data, and measured benchmark results. | Not Started
Suggested repository structure
databricks-data-engineering-journey/ ├── README.md ├── .gitignore ├── requirements.txt ├── python-foundations/ │ ├── week-01-etl-validation/ │ └── week-02-json-transformer/ ├── numpy-pandas/ │ ├── week-05-numpy-analytics/ │ └── week-06-customer-cleaning/ ├── pyspark/ │ ├── week-09-ingestion/ │ └── week-12-performance-lab/ ├── databricks/ │ ├── week-15-delta-merge/ │ ├── week-16-medallion-pipeline/ │ └── week-20-workflows/ ├── capstone/ │ ├── notebooks-or-src/ │ ├── tests/ │ ├── docs/ │ └── architecture/ └── notes/
Sample README starter
# Databricks Data Engineering Journey A six-month, 26-week learning portfolio covering Python, NumPy, Pandas, PySpark, Databricks, Delta Lake, testing, orchestration and performance optimization. ## Goals - Practice approximately 10 hours per week. - Build weekly mini-projects with tests and documentation. - Complete an end-to-end lakehouse capstone. ## Repository structure - `python-foundations/`: Python exercises and utilities - `numpy-pandas/`: local data analysis and cleaning - `pyspark/`: distributed transformations and performance labs - `databricks/`: notebooks and Delta Lake projects - `capstone/`: end-to-end project, tests and architecture - `notes/`: concise learning notes and interview preparation ## Safety Only use synthetic, public, or otherwise authorized data. Never commit passwords, tokens, credentials, employer/client data, or proprietary code. ## Progress Update this README as weekly deliverables are completed.